## Slide 1: Julkaisusuunnittelu
Suunnittelumekanismit pidemmällä aikavälillä
Erkki Pöyhönen & Maaret Pyhäjärvi
Nimeä | Attribution (Finland)
  http://creativecommons.org/licenses/by/1.0/fi/
  http://creativecommons.org/licenses/by/1.0/fi/deed.en

## Slide 2: Julkaisusuunnittelu
Julkaisun laajuudessa ei tehdä tarkkaa suunnitelmaa, mutta silti suunnitellaan
Mekanismina tuotteen työlista (product backlog) sekä tieto kehityksen nopeudesta (velocity)
Voidaan arvioida koska julkaisuun tarvittavat ominaisuudet ovat saatavilla ja arvion tarkkuus paranee tekemisen aikana

## Slide 3: Testing in the Product Backlog
Product Backlog is a delivery plan for the project
  It describes ”value items” – when given to customer, they’d find real use / value in this
  Items are in absolute priority order
Items typically have a concept of ”size”
  Either ”comparable enough”, story points or quick effort estimates
Based on the sized items in the product backlog becoming done, you can follow velocity – a way of evaluating realism of plans for future
Product backlog should not have separate testing items, but testing should be seen as essential part of everything asked of the teams

## Slide 4: Example: Roles and Responsibilities Towards PBL
R&D Project Manager
Product Manager(s)
Area Architect
Product Architect
Lead QE
Scrum Master
PBL
ABL(s)
Owns priorities for both
Decides order of items
Puts all his items to PBL
PBL “secretary”
Organizes backlog reviews and meetings
Puts new items to PBL identified in R&D
Splits items in PBL according to rules
Moves appropriate items to ABL(s)
Responsible for quality and size of items as basis for delivery planning
Collects metrics, updates burndown
ABL consistency
Analysis of implied architectural dependencies cross-team
Technical facilitation, technical scope negotiation
Identify tangible delivery items to ABL
Split PBL items for “our area” deliveries, checking others have taken there parts
Adding new innovative ideas that could be done within the area is encouraged
Maintains knowledge of “new items not yet communicated”

## Slide 5: Example: Product Backlog Reviews
Roadmap Commitment Review
When preparing a new roadmap
Purpose:
  Address Roadmap feasibility against items in PBL
  Agree velocity and buffer based on metrics, see if planned releases seem reasonable
For PdM/PgM/PjM/ R&Dmgmt
Planning day
Demo day
PBL Priority Review
Before planning day, “preplanning”
Purpose:
  Provide PdM information about risks in choices of priorities
  Provide teams guidance on why priorities are as they are
For SMs
Commitment Review
After planning day
Purpose:
  Agree on what WinCore-project will deliver on level of PBL though ABLs
  Make all work to be done visible
For SMs
Status Review
On weekly basis against monthly commitment
Purpose:
  Continuous visibility to likeliness to complete committed items
  Visibility to added items leaking to sprint
  Contingency planning, considering sprint cancellation
For SMs
New Item Review
When new items (blue) in PBL close to two weeks
Purpose:
  Identify which teams would need to react in ABLs for PBL items
  Communicate idea of wish-release by PdM
For SMs/AAs
Backlog Synchronization Review
Monthly check of plans of other part of system (Mgmt Systems & Research)
Purpose:
  Understand dependencies and optimization opportunities, synching roadmaps
  Resolving conflicts in priorities
For PjMs/ PgMs/ PdMs

## Slide 6: Quality in Agile Development
Release-ready known quality available at end of each iteration
  Defining done as ready for real use with agreed checks
Shared code ownership with Executable unit tests as documentation
  Avoiding specialized knowledge
Avoiding debt-taking on quality
  Fix problems before implementing new features
  Continuous regression testing as feedback mechanism

## Slide 7: Planning Testing without Planning the Details - On Effort Planning
Team plans efforts for the sprint during the planning day and checks which items from product backlog can be done with the resourcing limitations fixed for the sprint
Team views future items on rough sizing
  Problem and a workaround: traditional planning lead to huge amounts of time going into future planning  introduced a group of experts doing quick quesstimates that are not commitments
Commitment only one sprint at a time – enables more reliable planning than with traditional methods with visibility of real progress
If you need expensive environments, new recruits or something that just takes calendar time, that you may want to start earlier

## Slide 8: Having All Work Done within an Iteration
While much of the testing must and will fit an iteration, it is highly likely that some will not
  ”The System View” – functional and non-functional aspects of the real environment of use
Work not done should be made visible
  Not marking a product backlog item done before the work is completed or introducing new items if the value can be chosen not to be included (risk-taking view)
Promoting code for further system testing in next iteration:
  Exploratory testing: what did we miss while focusing on delivery; bugs, features, opportunities for improvement
  Combination/interaction testing, system regression testing: the latest added feature with all the others
  Scenario testing: Real-life use for stakeholders with the system as it is now
  Reliability / Endurance: Long-term use
  Performance testing: System Capabilities

## Slide 9: Defining a Delivery Increment from a Testing Point of View
The upcoming delivery increment is planned based on topmost items in the product backlog
Review the topmost items
  Is there all work represented that you know that would need to happen?
  Are risky features towards a release you know will happen in future in their appropriate priorities or at least, implications of choices known?
  Are the product backlog item sizes representative so that the assumptions of what will fit have a chance of being close to true?
  Is all types of work included, also the “just testing” things: quality debt, release efforts?
  Is the product owner aware of dependencies that could have cost change implications based on prioritization so that he can decide based on RoI?
The PBL items should define what is needed and why – leave all planning details for teams. Very rough guess of effort is sufficient in long-term planning.

## Slide 10: How to Tackle Fixed Bid Problems in Agile?
Before start of project
Create a product backlog
Size the items roughly (relative sizing), avoid making work breakdown, focus on understanding the customer intent
Make a guess on the velocity and check that the schedule would seem possible with that velocity to this plan
Make a fixed bid with the amount in product backlog plus some buffer in effort
During the project
Work only on items coming to you through the product backlog
In each planning day, compare the true plan to the product backlog expectation
At each demo, compare the true velocity to needed to complete the items in the product backlog
Mark in product backlog new items coming in and use change control mechanisms to change the fixed bid if needed
The customer gets better visibility with just as much certainty to the fixedness as before

## Slide 11: Ideoita, ajatuksia, kysymyksiä?